## Instructions for completion
SKYLARK PATHWAY: PRACTITIONER LED PROFESSIONAL LEARNING (SKYLARK) REPORT
1
Provider Name | 2
UKPRN | 3
Lead Name | 4
Reference Number
Instructions for completing the report
Please ensure all details are up to date when submitting. It is essential that the Project Lead keeps the report up-to-date throughout the programme. We suggest you use this report as a live document in a shared place.
We have designed this report with two different types of answers:
Required data and progress on programme - these are highlighted in grey and often require numbers.
Comment boxes (we highly encourage you to use these to provide further commentary) - these are always coloured in light blue.
Overall Summary
This section is to show the overall progress across the reporting period.
We will ask you to report on (1) Project activity - planned and actual - and (2) Practitioner engagement with professional learning events
As the project lead you will need to meet and/or communicate with the project team members to get update information on project progress. It might be helpful to create this report as a live shared document, so project team members can be kept updated.
Risk
The risk tab is where you document any risks associated with the APP Practitioner-led Professional Development (Skylark) programme. Please consider all related activities and ensure this tab is comprehensive in identifying and documenting how you manage risk. Obvious examples include meeting milestones and budget spend. Each risk shall have an ID (1,2,3…) and risk owner (most likely the project lead). Risks should be documented concisely and detail what the risk is (description) as well as the cause(s) and effect(s). Each risk shall be scored on impact and likelihood using a scale of 1-5 (1.Low and 5.High). The overall risk rating and score is then auto filled with the pre-populated formulas in the related cells. Planned mitigations with relevant dates shall then be documented resulting in a post mitigation score (impact x likelihood) that hopefully reduces the risk rating and score to a level as low as reasonably practicable.
Budget
This is where you outline the spend of the grant for the duration of the programme and monitor actual spend against the forecast.
Register
This is where you add the details of each of the 50 participants who engage with your Skylark professional learning events.

## Overall Summary
SKYLARK PATHWAY: PRACTITIONER LED PROFESSIONAL LEARNING (SKYLARK) REPORT
Overall Summary
Project Team Summary
| Name | Contact email | Job role | Job title | Organisation
Project Lead
Team member 1
Team member 2
Team member 3
Team member 4
Month | Activity | Lead Organiser | Attended by X people | Register tab completed - yes/no
2021-09-01
2021-10-01
2021-11-01
2021-12-01
2022-01-01
2022-02-01
2022-03-01
Planned activity for September 2021 | [5 empty] | Actual activity for September 2021
Planned activity for October 2021 | [5 empty] | Actual activity for October 2021
Planned activity for November 2021 | [5 empty] | Actual activity for November 2021
Planned activity for December 2021 | [5 empty] | Actual activity for December 2021
Planned activity for January 2022 | [5 empty] | Actual activity for January 2022
Planned activity for February 2022 | [5 empty] | Actual activity for February 2022
Planned activity for March 2022 | [5 empty] | Actual activity for March 2022
Note on C16: Add additional rows if needed.

## Risk
SKYLARK PATHWAY: PRACTITIONER LED PROFESSIONAL LEARNING (SKYLARK) REPORT
1. Low
2. Low - Medium
3. Medium
4. Medium to High
5. High
Risk and RAG rating
Please consider all elements of the programme and the risk attached to hitting the grant milestones
1 - Low | 2 - Low to Medium |  |  |  | 3 - Medium |  | 4 - Medium to High |  | 5 - High
Successful completion of milestones on time, cost and quality appears highly likely and there are no outstanding issues that appear to threaten the appropriate spend of the grant at this stage. | Successful completion of milestones on time however there are a few areas which will need to be monitored to ensure appropriate spend of the grant is not threatened. |  |  |  | Successful completion of milestones appear probable however there are a few concerns which will require constant attention to ensure appropriate spend of the grant is not threatened. |  | Successful completion of milestones are in doubt with a number of major risks or issues apparent impacting on the appropriate soend of the grant. Urgent and immediate action is needed to ensure these are addressed and determine if resolution is feasible. |  | Successful completion of milestones appear unachievable - major issues do not appear to be manageable or resolvable or a reassessment of viability may be needed to ensure appropriate spend of the grant.
Please select a RAG rating from the dropdown for the whole programme considering the guidance above | [5 empty] | 4. Medium to High
Comments
Please explain why you have chosen the above rationale
Comments
Please list any key challenges or risks for the reporting period
Risk Register
Please review and update quarterly, or more regularly if there are significant changes to the Grant or risks. When assessing likelihood and impact please use the rating of 1-5, with 5 showing high impact or high likelihood.
Risk - event, cause and effect |  |  |  | Current Risk Rating | Planned mitigating actions |  | Date of Review | Status Update | Following update…
Risk There is a risk that (description) which could be the result of (causes) that may lead to (impacts) | Impact (out of 5) | Likelihood (out of 5) | Risk Rating | Score | Planned mitigations | Target date |  |  | Impact (out of 5) | Likelihood (out of 5) | Risk Rating | Score | Date of next Review
Example: There is a risk that network attendance may be impacted if we go into lockdown. | 4 | 3 | 12 | Critical / Possible | All network events have been designed as online events. | 2021-03-21 | 2021-01-21 |  | 1 | 1 | 1 | Negligible / Very Unlikely
Note on B8: ====== ID#AAAANHx6Yes Jaya Varsani (2021-07-22 08:41:00) Will need to give guidance on how to fill out risk register. Can give examples with mitigating circumstances and they can then add in their own

## Budget
SKYLARK PATHWAY: PRACTITIONER LED PROFESSIONAL LEARNING (SKYLARK) REPORT
Budget
The Grant may be used to contribute towards the following activity costs: 1. The cost of reducing the project team's teaching timetable so they can undertake the Skylark CPD and run professional learning events for a minimum of 50 unique practitioners. Professional learning events must consist of: - a series (minimum 3) of online Ideas Rooms/action learning sets and - a minimum of two AP-led networks: one in the autumn term (Oct - Dec 21) and one in the spring term (Jan - Mar 22) N.B The AP-led networks can include knowledge exchange activity e.g.: #FESwapShop 2. Administrative costs of the Project Lead who will support team members, monitor/support attendance at Skylark online CPD event/s, and complete a monthly performance report for touchconsulting; 3. The travel costs of the Project Lead and team members to arrange/run in-person and online professional learning events 4. Other appropriate costs as agreed with touchconsulting.
You are required to complete the relevant columns below. The budget will reflect a detailed breakdown of the utilisation of the Grant. You are expected to complete the Spend to Date each month. Please ensure you keep all evidence of spend for auditing purposes.
Activity | Budget Costs (to be completed at the start and not changed) | [7 empty] | Total spend of the grant | Remaining grant to spend | Comments (will you spend the budget amount? If not we can look to revise the grant allocation.)
|  | Report 1: Sep | Report 1: Oct | Report 2: Nov | Report 3: Dec | Report 4: Jan | Report 5: Feb | Report 6: Mar
Remission for project lead, including administrative activity. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remission for project team member 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remission for project team member 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remission for project team member 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remission for project team member 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel costs for project lead/team |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Other costs (to be agreed with touchconsulting) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Any additional notes regarding above budget, spend to date, forecast or final spend.

## Register
| Name of practitioner | Email address | Job title | Organisation | Ideas Room/ALS 1 | Ideas Room/ALS 2 | Ideas room/ALS 3 | AP-led Network 1 (Autumn term) | AP-led Network 2 (Spring term) | You will need to update this register monthly to evidence the practitioners who have engaged in your Skylark professional development events. Feel free to add additional columns to represent additonal Ideas rooms/ALS and/or AP-led Networks
1 | Nasreen Shaid | n.shaid@XXXXXX.com | Engineering tutor | Pierre Pont | y - 31.08.21 |  |  | y - 8.09.21
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Note on B1: There should be a total of 50 practitioners recorded by 31 March 2022 recorded in column B.
Note on C1: Add the practitioner's email address. They will not be contacted by ETF.
Note on D1: Joss Kang: Add the practitioner's job title.
Note on E1: Joss Kang: Add the organisation the practitioner is employed by.
Note on F1: If the practitioner has particpated in an Ideas Room/ALS please indicate with a Y. OPTIONAL: You may wish to record the date as well.
Note on G1: If the practitioner has particpated in a second Ideas Room/ALS please indicate with a Y.
Note on H1: If the practitioner has particpated in a third Ideas Room/ALS please indicate with a Y.
Note on I1: If the practitioner has particpated in an AP-led network please indicate with a Y.
Note on J1: If the practitioner has particpated in the 2nd AP-led network please indicate with a Y.